## Sheet1
Category | Story Desc | Status
Infra | Install & connect Django, Mongodb | Done
Admin | Enable admin site | Done
Admin | Add Question & Tag models and enable data entry; Question with 4 options as text, | Done
Admin | Tags as 1-Many relationship to Question | Done
Customer Facing | Enable Questions display | Done
Customer Facing | Enable Questions to come one after the other; same not to repeat for that user | Done
Customer Facing | Enable Tags list to display | Done
SEO | when tag is clicked Questions for that tag to come only, URL should change to include actual tag name | Done
Customer Facing | Enable remembering of which user has seen what questions at tag level | Done
Customer Facing | Ability to answer the question and display correct answer along with information | Done
Admin | Ability to Question to have input answer versus multiple choice text
Customer Facing | Ability to display and correct input answer type questions
Admin | Contributed by in Admin for Question should auto populate from user adding question | Done
SEO | Ability to add links in information of Questions
Admin | 2 roles for admin site, one who could just add questions and other who can do everything (users, tags etc.) - superuser
Analytics | Basic site stat collection - visitors, total questions seen, attempted, correct
Analytics | Basic question stat collection - seen, attempted, correct
Admin | Display page for site stat
Admin | Display page for User (only that user can see) where some stats shown - how many questions contributed, visisted and correctly answered
SEO | POC to see if url can be chnaged (context of question) for each question
Customer Facing | create url pattern / capability to see questions contributed by a particular user
Admin | create tempQuestion model | Done
Admin | Change question adding by users to tempQuestions
Admin | Add ability to let super user move/approve temp question to question
Analytics | Add stat of how many temp uploaded, approved to user stat page
Infra | Harden DB passwords and any other for MVP launch
Infra | Harden HTTPs etc. an another things for MVP launch
Infra | Explore use of front end framework - node.js bootstrap.js etc.
UI | UI improvement for Question display
UI | UI imporvement for Tag display
UI | UI improvement for User stat Display
UI | UI improvement for tempQuestion Add
SEO | Generate SiteMap and auto triggers with new url / questions
Infra | Register domain
Infra | Evaluate cloud sol - AWS, rackspace tec.
Infra | Launch MVP on cloud sol